## Status Track
Project Status Check Report Team - 10
Sl no. | Employee ID | Name | Domain | Module | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 29-02-2022
|  |  | Back-end | Login | ER Diagram ,Database, Division of domain | Model,Repository | Service, Controller | Exception,Integration | Login Components
1 | 2583056 | Syed Mohammed Akram | SpringBoot | HomePage,AboutUs,DB schema,View bookings | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
2 | 2583218 | Thotakuri Malavika | SpringBoot | Search and add passengers | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
3 | 2583025 | U Santhosh | SpringBoot | User login,ContactUs,User registration | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
4 | 2582768 | Varshini X | SpringBoot | View all bus details,Remove and update details | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
5 | 2583852 | Vishnukumar Balasubramani | SpringBoot | View all users,View all Bookings | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
6 | 2583617 | Yanamaladoddi Lekhya | SpringBoot | View user details,Update user details | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition
7 | 2583557 | Yendamuri Gokulesh | SpringBoot | Admin login,Admin dashboard | discussion and analysing the project | started the front end part and the back end | completing the front end | completing the back end | integrating the application | completing the ppt | final submition

## Status Meeting
Status Meeting Group - 10
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2020-02-23 | 9:45 | a | 2:45 | a | 6:00 | a
2020-02-24 | 9:45 | a | 2:30 | a | 6:00 | a
2020-02-25 | 9:45 | a | 2:00 | a | 6:00 | a
2020-02-26 | 9:00 | a | 2:45 | a | 6:00 | a
2020-02-27 | 9:45 | a | 2:30 | a | 6:00 | a
2020-02-28 | 9:45 | a | 2:30 | a | 6:00 | a
2020-02-29 | 9:45 | a
2020-03-01
2020-03-02
2020-03-03

## Lead
Online Bus Booking System
Group Number - 10
Team Lead : Yendamuri Gokulesh